## Sheet1
Activity List
WBS no. | Description | Dependency Type | Duration | Responsible
Goal Pro
0 | Go ahead from the client
1 | Mobile
1.1 | Android
1,1,1 | UI
1,1,1,1 | Design Login | Depend on Client go ahead | 1 | Wade
1,1,1,2 | Design Register | Depend on Client go ahead | 1 | Wade
1,1,1,3 | Design Home Page | Depend on Client go ahead | 1 | Wade
1,1,1,4 | Design Daily Quote Page | Depend on Client go ahead | 1 | Wade
1,1,1,5 | Design Upload Page | Depend on Client go ahead | 1 | Wade
1,1,1,6 | Design CV/Life Skills Page | Depend on Client go ahead | 1 | Sachin
1,1,1,7 | Design Achievements Page | Depend on Client go ahead | 1 | Sachin
1,1,2 | Functionality
1,1,2,1 | Build Login | Dependent on API Post Login Method | 2 | Wade
1,1,2,2 | Build Register | Dependent on API Post Register Method | 2 | Wade
1,1,2,3 | Build Home Page | Dependent on API GetGoals Method | 2 | Wade
1,1,2,4 | Build Daily Quote Page | Dependent on API Get Daily Quote Method | 2 | Wade
1,1,2,5 | Build Upload Page | Dependent on Firebase Storage | 2 | Wade
1,1,2,6 | Build CV/Life Skills Page | Dependent on API POST UpdateCV method | 2 | Sachin
1,1,2,7 | Build Achievements Page | Dependent on API Post Achievements Method | 2 | Sachin
1.2 | IOS
2 | Website
2.1 | UI
2,1,1 | Design Login | Depend on Client go ahead | 1 | Joseph
2,1,2 | Design Register | Depend on Client go ahead | 1 | Joseph
2,1,3 | Design Home Page | Depend on Client go ahead | 1 | Joseph
2,1,4 | Design Daily Quote Page | Depend on Client go ahead | 1 | Joseph
2,1,5 | Design User Statistics Page | Depend on Client go ahead | 1 | Joseph
2.2 | Functionality
2,2,1 | Build Login | Dependent on Database | 2 | Jarrod
2,2,2 | Build Register | Dependent on Database | 2 | Theasan
2,2,3 | Create Home Page | Dependent on Database | 2 | Jarrod
2,2,4 | Create Daily Quote Page | Dependent on Database | 2 | Theasan
2,2,5 | Create User Statistics Page | Dependent on Database | 2 | Jarrod
3 | API
3.1 | Get Request | Dependent on Database | 10 | Jarrod
3.2 | Post Request | Dependent on Database | 10 | Jarrod